## Slide 1: Client Impact Assessment Roadmap
 | 2026 |  |  |  | 2027 |  |  |  | 2028 | 
 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
Billing Files |  |  |  |  |  |  |  |  |  | 
Eligibility Files |  |  |  |  |  |  |  |  |  | 
Benefits |  |  |  |  |  |  |  |  |  | 
Help Desk / Operational Support |  |  |  |  |  |  |  |  |  | 
Reporting |  |  |  |  |  |  |  |  |  | 
Vendor Engagement |  |  |  |  |  |  |  |  |  | 
ID cards |  |  |  |  |  |  |  |  |  | 
Claims Adjudication Data Flow (CADF) Testing |  |  |  |  |  |  |  |  |  | 
Last Updated: 07/17/2026
Dates Subject to Change
The below illustrates swim lanes or impacts across all clients. Client-specific impacts will not be covered as part of this roadmap view but will be shared as part of an individual client's project plan as applicable.
Eligibility Impacts Confirmed
Billing File Impacts Finalized & Published
Preliminary Billing File Layouts Available
Final Billing File Layouts Released
Billing File Test Window Open
Validation Sign‑Off / Risk Acceptance
Post‑Transition Monitoring Begins
Eligibility File Layouts Shared
Benefit‑Related F6 Impacts Identified
Benefit Template Layouts Shared
Batch Testing Tool / Scenarios Available
Operations Testing Complete
Help Desk Impact Scope Defined
Client‑Facing Support FAQs & Talking Points Delivered
Help Desk Demo / Training Window Begins
Help Desk Training Window Ends
Transition‑Period Monitoring
Reporting Impact Inventory Published
Updated Reporting Specifications Available
Parallel Reporting Testing Begins
Reporting Reconciliation Complete
Reporting Sign‑Off / Risk Acceptance
Post‑Transition Reporting Review
Vendor Impact Expectations Communicated
Vendor Inventory & Ownership Confirmed
Vendor Readiness Confirmed
Vendor Testing (if applicable)
Vendor Risk Mitigation Finalized
Vendor Steady‑State Confirmed
CADF Scope & Expectations Communicated
CADF Testing Window Open
CADF Validation Complete
CADF Issue Triage & Resolution
Pharmacy notification being sent re: IIN transition
ID card reprints to reference IIN and 8-digit values
Final Eligibility File Specifications Released
Client Billing Layout Decision Due
Begin Accepting Client Eligibility Layout Decisions
CADF Client List Defined
Define New Client CADF impacts
Operations Testing
Window Open
Critical Activities
Legend:
Critical Milestone
Client Milestone
Client Eligibility Layout Decision Due
* Eligibility Testing occurs on a rolling basis as Client Decisions are received
PBM Milestone
Shared Milestone
* Billing File Testing occurs on a rolling basis as Client Decisions are received
Eligibility file test window open
Validation Sign‑Off / Risk Acceptance
Post‑Transition Monitoring Begins
Go-live support
Client notification of upcoming pharmacy comm
provide IIN values for Carriers/Contracts

## Slide 2: Appendix
Below is a table describing the various swim lanes outlined in the roadmap slide
Impact Category | Description
Benefits | Milestones that impact benefit configuration inputs (e.g., prior authorization, accumulator data), automation feeds, and intent templates that impact adjudication
Billing Files | File layouts where clients/vendors receive claim/billing data (e.g., CDL, PAL) from ESI
Eligibility Files | File layouts where ESI receives eligibility data from clients/vendors
Help Desk / Operational Support | Milestones that impact call center agents and their interactions with pharmacies and members (i.e., talking points, SOPs)
Reporting | Milestones that impact the various claim-level reports either provided directly to client or that clients can self-service using Evernorth Control Center
Vendor Engagement | Coordination with vendors or third-party partners who manage reporting or file transfers
ID Cards | ID cards should reference 8-digit IINs with any scheduled reprint efforts starting 1/1/2027
Claims Adjudication Data Flow (CADF) Testing | Critical phase of Client Testing involving anything that impacts claims adjudication* to ensure core business/claims data flows through internal and client systems as expected